|  |  |
| --- | --- |
| Sponsoring Organization (SO) |  |

## Launch Stage

|  |  |
| --- | --- |
| **Timeframe** | **Early Literacy Interim Review Step or Activity** |
| 3 months before Launch session | DESE notifies SO of its review timeline   * After notification: Appoint review designee * After notification: Confirm timeline for the review |
| March 20XX  (specific date based on Doodle Poll) | **Interim Review Cohort Launch Session (virtual)**   * Review designee and up to 5 team members attend session * DESE specialist will schedule virtual meeting and send calendar invite * DESE specialist will share [Early Literacy Matrix](https://www.doe.mass.edu/edprep/review/toolkit/informal/early-literacy-matrix.docx)   **After Launch Session, start working on:**   * Launch Worksheet * Early Literacy Matrix * Program Overview * Candidate Artifacts * Required Documents * Coordination with DESE on early literacy course observation * Survey recruitment   **Due date: ENTER DUE DATE (12 weeks after Launch Session)** |

## Initial Inquiry Stage

|  |  |
| --- | --- |
| **Timeframe** | **Early Literacy Interim Review Step or Activity** |
| By April 1, 20XX | DESE will share survey links and template language for recruitment |
| 8 weeks before Focus Group & Interview Days | **Initial Inquiry Technical Assistance (TA) Call**   * DESE specialist will schedule virtual meeting to discuss focus groups, interviews, and observations   **After TA Call, start working on:**   * SO-approved focus group and interview day schedule   **Due date: ENTER DUE DATE (10 business days after TA Call 3 or sooner)** |
| August/ September | DESE approves focus group and interview day schedule and sends survey links  **After DESE approval, start working on:**   * Focus group recruitment * DESE specialist will schedule 20 minute virtual Pre-Observation Meeting and send calendar invite * Course Observations   **As recruitment progresses, start documenting:**   * Evidence of recruitment * List of anticipated focus group participants   **Evidence of recruitment and list of anticipated focus group participants due date: ENTER DUE DATE – 2 weeks before focus groups** |
| September 15, 20XX | Stakeholder Surveys Close |
| Month 13 | Focus Group and Interview Days  (1-3 days)   * Stakeholders participate in focus groups and interviews |

## Follow Up Inquiry Stage

|  |  |
| --- | --- |
| **Timeframe** | **Early Literacy Interim Review Step or Activity** |
| No later than one month after the focus group/intervein days | **Follow-Up Inquiry Technical Assistance Call**   * DESE specialist will schedule virtual meeting to review the targeted submission worksheets and additional requests for the Follow-Up Inquiry submission   **After TA Call, start working on:**   * Targeted submission worksheets * Requested documents or artifacts   **Due date: ENTER DUE DATE (12 weeks after TA Call)** |

## Determination Stage

|  |  |
| --- | --- |
| **Timeframe** | **Early Literacy Interim Review Step or Activity** |
| May/June | DESE issues Factual Accuracy draft report  **After receiving Factual Accuracy draft report, start working on:**   * Identifying any factual inaccuracies in draft report   **Due date: ENTER DUE DATE (10 business days after FA draft released)** |
| By June 30, 20XX | DESE issues Final Approval Status and Report |